## Sheet1
|  |  | 52 | weeks
hours | rev |  | 26 | sprints
208 | 28080
416 | 72800
2080 | 270400
416 | 16224
2080 | 65520
2080 | 65520
2080 | 65520
9360 | 584064
| 22464 | sprint price
| 62.4 | blended rate

## Sheet2
| Report | Review Requirements | Front End Mock Ups | Back End | QA Ready | Business Sign Off | Production Ready
1 | FLR - Subs and Pens | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 4 | Sprint 1
2 | FLR - Calls | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 4 | Sprint 2
3 | FLR - AoD | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 4 | Sprint 3
4 | FLR - Activity Tracking | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 4 | Sprint 4
5 | FLR - CG Attendance | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 4 | Sprint 4 | Sprint 5 | Sprint 5
6 | FLR - CG Turnover | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 4 | Sprint 4 | Sprint 5 | Sprint 6
7 | FLR - Client Usage | Sprint 3 | Sprint 3 | Sprint 4 | Sprint 4 | Sprint 4 | Sprint 5 | Sprint 7
8 | EIA - Dashboard | Sprint 2 | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 4 | Sprint 8
9 | EIA - Ops Dashboard | Sprint 4 | Sprint 4 | Sprint 5 | Sprint 5 | Sprint 5 | Sprint 6
10 | Client Usage Analysis | Sprint 3 | Sprint 5 | Sprint 5 | Sprint 5 | Sprint 5 | Sprint 5
11 | KP & RPN GP Pipeline | Sprint 3 | Sprint 5 | Sprint 5 | Sprint 5 | Sprint 5 | Sprint 6