## Stakeholders
Home Office Feedback Stakeholders
Tim Shanahan | tshanahan@homeinsteadinc.com | Engage early throughout the project. Mockups, Demos, prioritization
Cory Jensen | cory.jensen@homeinsteadinc.com
Kiley Drog | kiley.drog@homeinsteadinc.com
Amy J. Smith | amy.jsmith@homeinsteadinc.com
Sandip Ghotikar | Sandip.Ghotikar@homeinsteadinc.com
Kerri Nikunen | kerri.nikunen@homeinsteadinc.com
Mike Brownfield | mike.brownfield@homeinsteadinc.com
Jessica Schultz | jessica.schultz@homeinsteadinc.com
Kimberly Griffith | kimberly.griffith@homeinsteadinc.com
Maria Reid | maria.reid@homeinsteadinc.com
Home Office DnA Stakeholders
Jacob Kalstrup | jacob.kalstrup@homeinsteadinc.com | Engage for reporting & Data needs
Steve Fritton | steve.fritton@homeinsteadinc.com
Kelli Gustafson | kgustafson@homeinsteadinc.com
Jim Shaal | jim.shaal@homeinsteadinc.com
Ruiqi Wang | ruiqi.wang@homeinsteadinc.com
Home Office Informed Stakeholders
Matt Hurley | matt.hurley@homeinsteadinc.com | Keep Informed of progress
Amanda Johnson | amanda.johnson@homeinsteadinc.com
Carrie Meyer | carrie.meyer@homeinsteadinc.com
Lisa Weber | lisa.weber@homeinsteadinc.com
Dar Andrews | dar.andrews@homeinsteadinc.com
Vicki Castleman | vcastleman@homeinsteadinc.com
Julie Jacobson | julie.jacobson@homeinsteadinc.com
Tye OsBurn
Brett Wilmeth | brett.wilmeth@homeinsteadinc.com
Jennifer Sonderman | jsonderman@homeinsteadinc.com
Franchise Feedback Stakeholders
Name | Email | Franchise | Role | Engage later in completed demos
Matt Cohn | mcohn@homeinsteadla.net | Baton Rouge | Owner
Sandy Hull | shull@homeinsteadla.net | Baton Rouge | GM
Bill Dahlquist | bill.dahlquist@homeinstead.com | Denver | Owner
Matt Clark | matt.clark@homeinstead.com | Denver | GM
Cameo Allred | cameo.allred@homeinstead.com | Fresno | KP
Victor Boyd | victor.boyd@homeinstead.com | Venice FL | GM
Aimee Moreland | aimee.moreland@homeinstead.com | Belleville IL 299 | GM
Noah Kraljev | noah.kraljev@homeinstead.com | Belleville IL 299 | Client Care Coordinator
Paula Quinones | paula.quinones@homeinstead.com | Belleville IL 299 | Client Care Coordinator

## Sheet1
RACI Matrix | [21 empty] | Roles and Responsibilities
BRIDGES Reporting - Data Acceleration POD | [21 empty] | Responsible, Accountable, Consulted, Informed
|  | ROLES | Vicki Castleman | Dar Andrews | Lisa Weber | Jim Shaal | Julie Jacobson | Devang Pandya | John Harvey | Steve Fritten | Rob Jeltema | Thad Stanfill | David Compton | Offshore Team | Arun Chaturvedi | Jacob Kalstrup | Tye OsBurn | Brett Wilmeth | Kelli Gustafson | Ruiqi Wang | Jacob Kalstrup | Jennifer Sonderman | Matt Hurley | Home Office and Franchise Stakeholders
| Deliverable or Task | Status | Sponsor / Leadership | [6 empty] | Project Team | [6 empty] | Other Resources
Sprint 0
| Backlog Release Plan |  | I | I | I | C | I | I | I | R | R | C | C | I | I | C | I | i | C | C | C | I | I | I
| Scope Data Quality Cleansing efforts |  | I | I | I | C | I | I | I | C | C | R | R | I | I | C | I | i | C | C | C | I | I | I
| Scope Google Big Query Migration |  | I | I | I | C | I | I | I | C | C | R | R | I | I | C | I | i | C | C | C | I | I | I
| Consume existing data architecture |  | I | I | I | C | I | I | I | C | C | R | R | I | I | C | I | i | C | C | C | I | I | I
Sprints 1 through 8
| Daily Scrums |  | I | I | I | C | I | I | I | R | C | I | I | I | I | C | I | I | I | I | I | I | I | I
| Weekly Status Reports |  | I | I | I | C | I | I | I | R | C | S | I | S | R | C | I | I | C | C | C | I | I | I
| Sprint Planning |  | I | I | I | C | I | I | I | A | A | S | S | I | I | C | I | I | C | C | C | I | C | C
| Iterative Development |  | I | I | I | C | I | I | I | A | R | S | S | R | I | A | I | I | C | C | C | I | C | C
| Operationalize |  | I | I | I | A | I | I | I | A | R | R | R | S | I | A | I | I | A | A | A | I | C | C
| Transition |  | I | I | I | A | I | I | I | C | A | R | S | S | I | A | I | I | R | R | R | I | C | C
| Work Acceptance |  | I | I | I | A | I | I | I | R | R | I | I | I | I | A | I | I | A | A | A | I | C | C
D | Driver | Assists those who are responsible for a task.
R | Responsible | Assigned to complete the task or deliverable.
A | Accountable | Has final decision-making authority and accountability for completion. Only 1 per task.
S | Support | Provides support during implementation.
C | Consulted | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action.
I | Informed | Must be informed after a decision or action.

## Sheet2
TEK Team | Role | HISC Stakeholders | Role
John Harvey | Business Development Manager | Vicki Castleman | VP, Performance Solutions
Brad Dubisar | Account Manager | Dar Andrews | VP, Technology
Arun Chaturvedi | Customer Success Lead | Lisa Weber | Sr. Product Manager
Thad Stanfill | Practice Architect | Jim Shaal | Sr. Manager, Data Analytics
David Compton | Data Analyst | Rob Jeltema | Product Owner
Offshore Team | Offshore Mngr and Data Engineers | Steve Fritton | Delivery Manager